## cd_dashboard
custom_region_name | council_name | contract_name | contract_dno_regions | work_package_name | capex_bom | capex_installation | capex_connection | target_sites | target_sockets | contingency_percent | target_sockets_1 | target_sockets_2 | target_sockets_3 | target_sockets_4 | target_sockets_5 | target_sockets_6 | target_sockets_7 | target_sockets_8 | target_sockets_9 | target_sockets_10 | target_sockets_11 | target_sockets_12 | planned_sites | planned_sockets_1 | planned_sockets_2 | planned_sockets_3 | planned_sockets_4 | planned_sockets_5 | planned_sockets_6 | planned_sockets_7 | planned_sockets_8 | planned_sockets_9 | planned_sockets_10 | planned_sockets_11 | planned_sockets_12
SOUTH | Surrey | Surrey | UKPN_SE | Surrey WP10 | 150000 | 150000 | 150000 | 10 | 150 | 10 | 50 | 50 | 50 | [9 empty] | 165 | 55 | 55 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SOUTH | Surrey | Surrey | UKPN_SE | Surrey WP11 | 100000 | 100000 | 100000 | 10 | 100 | 10 |  |  |  |  | 50 | 50 | [6 empty] | 110 | 0 | 0 | 0 | 0 | 55 | 55 | 0 | 0 | 0 | 0 | 0 | 0
SOUTH | Surrey | Surrey | UKPN_SE | Surrey WP12 | 100000 | 100000 | 100000 | 10 | 100 | 10 | [5 empty] | 50 | 50 | [5 empty] | 110 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 0 | 0 | 0 | 0 | 0
SOUTH | Surrey | Surrey | UKPN_SE | Surrey WP13 | 100000 | 100000 | 100000 | 10 | 100 | 10 | [6 empty] | 50 | 50 |  |  |  |  | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 0 | 0 | 0 | 0
SOUTH | Surrey | Surrey | UKPN_SE | Surrey WP14 | 100000 | 100000 | 100000 | 10 | 100 | 10 | [7 empty] | 50 | 50 |  |  |  | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 0 | 0 | 0
SOUTH | Surrey | Surrey | UKPN_SE | Surrey WP15 | 100000 | 100000 | 100000 | 10 | 100 | 10 | [9 empty] | 50 | 50 |  | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 0
SOUTH | Surrey | Surrey | UKPN_SE | Surrey WP16 | 50000 | 50000 | 50000 | 10 | 50 | 10 | [11 empty] | 50 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55
SOUTH | Surrey | Surrey | UKPN_SE | Surrey WP17 | 0 | 0 | 0 | 10 | 0 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SOUTH | Surrey | Surrey | UKPN_SE | Surrey WP18 | 0 | 0 | 0 | 10 | 0 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SOUTH | Surrey | Surrey | UKPN_SE | Surrey WP19 | 0 | 0 | 0 | 10 | 0 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SOUTH | Surrey | Surrey | UKPN_SE | Surrey WP20 | 0 | 0 | 0 | 10 | 0 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SOUTH | Surrey | Surrey | UKPN_SE | Surrey WP21 | 0 | 0 | 0 | 10 | 0 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SOUTH | Surrey | Surrey | UKPN_SE | Surrey WP22 | 0 | 0 | 0 | 10 | 0 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SOUTH | Surrey LP | Surrey LP | UKPN_SE | Surrey Lamppost WP1 | 100000 | 100000 | 100000 | 10 | 100 | 10 |  |  |  | 50 | 50 | [7 empty] | 110 | 0 | 0 | 0 | 55 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SOUTH | Surrey LP | Surrey LP | UKPN_SE | Surrey Lamppost WP2 | 300000 | 300000 | 300000 | 10 | 300 | 10 | [5 empty] | 50 | 50 | 50 | 50 | 50 | 50 |  | 330 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 55 | 55 | 55 | 55 | 0
SOUTH | Surrey LP | Surrey LP | UKPN_SE | Surrey Lamppost WP3 | 100000 | 100000 | 100000 | 10 | 100 | 10 | [5 empty] | 50 | 50 | [5 empty] | 110 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 0 | 0 | 0 | 0 | 0
SOUTH | Surrey LP | Surrey LP | UKPN_SE | Surrey Lamppost WP4 | 100000 | 100000 | 100000 | 10 | 100 | 10 | [6 empty] | 50 | 50 |  |  |  |  | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 0 | 0 | 0 | 0
SOUTH | Surrey LP | Surrey LP | UKPN_SE | Surrey Lamppost WP5 | 100000 | 100000 | 100000 | 10 | 100 | 10 | [7 empty] | 50 | 50 |  |  |  | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 0 | 0 | 0
SOUTH | Surrey LP | Surrey LP | UKPN_SE | Surrey Lamppost WP6 | 100000 | 100000 | 100000 | 10 | 100 | 10 | [8 empty] | 50 | 50 |  |  | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 0 | 0
SOUTH | Surrey LP | Surrey LP | UKPN_SE | Surrey Lamppost WP7 | 100000 | 100000 | 100000 | 10 | 100 | 10 | [9 empty] | 50 | 50 |  | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 0
SOUTH | Surrey LP | Surrey LP | UKPN_SE | Surrey Lamppost WP8 | 100000 | 100000 | 100000 | 10 | 100 | 10 | [10 empty] | 50 | 50 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55
SOUTH | Surrey LP | Surrey LP | UKPN_SE | Surrey Lamppost WP9 | 50000 | 50000 | 50000 | 10 | 50 | 10 | [11 empty] | 50 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55
SOUTH | Surrey LP | Surrey LP | UKPN_SE | Surrey Lamppost WP10 | 0 | 0 | 0 | 10 | 0 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SOUTH | Surrey LP | Surrey LP | UKPN_SE | Surrey Lamppost WP11 | 0 | 0 | 0 | 10 | 0 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SOUTH | Plymouth | Plymouth | WPD_S | Plymouth WP1 | 111000 | 50000 | 50000 | 10 | 50 | 10 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SOUTH | Plymouth | Plymouth | WPD_S | Plymouth WP2 | 111000 | 100000 | 100000 | 10 | 100 | 10 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 55 | 55 | 0 | 0 | 0 | 0 | 0 | 0
SOUTH | Plymouth | Plymouth | WPD_S | Plymouth WP3 | 150000 | 150000 | 150000 | 10 | 150 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 0 | 0 | 0 | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 55 | 0 | 0 | 0
SOUTH | Plymouth | Plymouth | WPD_S | Plymouth WP4 | 150000 | 150000 | 150000 | 10 | 150 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 0 | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 55 | 0
SOUTH | Plymouth | Plymouth | WPD_S | Plymouth WP5 | 30000 | 50000 | 50000 | 10 | 50 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55
SOUTH | Bournemouth, Christchurch & Poole | Bournemouth, Christchurch & Poole | WPD_S | Bournemouth, Christchurch and Poole WP1 | 195000 | 200000 | 200000 | 10 | 200 | 10 | [8 empty] | 50 | 50 | 50 | 50 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 55 | 55
SOUTH | Bournemouth, Christchurch & Poole | Bournemouth, Christchurch & Poole | WPD_S | Bournemouth, Christchurch and Poole WP2 | 0 | 0 | 0 | 10 | 0 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SOUTH | Bournemouth, Christchurch & Poole | Bournemouth, Christchurch & Poole | WPD_S | Bournemouth, Christchurch and Poole WP3 | 0 | 0 | 0 | 10 | 0 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SOUTH | Dorset | Dorset | WPD_S | Dorset WP1 | 195000 | 200000 | 200000 | 10 | 200 | 10 | [7 empty] | 50 | 50 | 50 | 50 |  | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 55 | 55 | 0
SOUTH | Dorset | Dorset | WPD_S | Dorset WP2 | 60000 | 50000 | 50000 | 10 | 50 | 10 | [11 empty] | 50 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55
SOUTH | Dorset | Dorset | WPD_S | Dorset WP3 | 0 | 0 | 0 | 10 | 0 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SOUTH | West Sussex | West Sussex | UKPN_SE | West Sussex - Phase 4 WP2 | 132000 | 250000 | 250000 | 10 | 250 | 10 | 50 |  | 50 |  |  |  | 50 | 50 | 50 |  |  |  | 275 | 55 | 0 | 55 | 0 | 0 | 0 | 55 | 55 | 55 | 0 | 0 | 0
SOUTH | Wealden | Wealden | UKPN_SE | Wealden | 18000 | 100000 | 100000 | 10 | 100 | 10 | 50 |  | 50 | [9 empty] | 110 | 55 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SOUTH | Havering | Havering | UKPN_LPN | Havering | 33000 | 100000 | 100000 | 10 | 100 | 10 |  | 50 |  | 50 | [8 empty] | 68 | 0 | 13 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SOUTH | Dorset - LEVI Pilot WP1 | Dorset - LEVI Pilot WP1 | WPD_S | Dorset - LEVI Pilot WP1 | 90000 | 50000 | 50000 | 10 | 50 | 10 | [6 empty] | 50 | [5 empty] | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0
SOUTH | Dorset - LEVI Pilot WP2 | Dorset - LEVI Pilot WP2 | WPD_S | Dorset - LEVI Pilot WP2 | 0 | 0 | 0 | 10 | 0 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Central & Wales | Windsor & Maidenhead | Windsor & Maidenhead | WPD_SM | Windsor & Maidenhead WPX | 0 | 0 | 0 | 10 | 0 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Central & Wales | West Berkshire | West Berkshire | WPD_SM | West Berkshire WP1 | 150000 | 200000 | 200000 | 10 | 200 | 10 |  |  |  |  | 50 | 50 | 50 | 50 |  |  |  |  | 220 | 0 | 0 | 0 | 0 | 55 | 55 | 55 | 55 | 0 | 0 | 0 | 0
Central & Wales | West Berkshire | West Berkshire | WPD_SM | West Berkshire WP2 | 157500 | 200000 | 200000 | 10 | 200 | 10 | [7 empty] | 50 | 50 | 50 | 50 |  | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 55 | 55 | 0
Central & Wales | West Berkshire | West Berkshire | WPD_SM | West Berkshire WP3 | 30000 | 50000 | 50000 | 10 | 50 | 10 | [11 empty] | 50 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55
Central & Wales | North Northamptonshire | North Northamptonshire | WPD_SM | North Northamptonshire WP1 | 180000 | 200000 | 200000 | 10 | 200 | 10 | [5 empty] | 50 | 50 | 50 | 50 |  |  |  | 220 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 55 | 55 | 0 | 0 | 0
Central & Wales | North Northamptonshire | North Northamptonshire | WPD_SM | North Northamptonshire WP2 | 165000 | 200000 | 200000 | 10 | 200 | 10 | [8 empty] | 50 | 50 | 50 | 50 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 55 | 55
Central & Wales | North Northamptonshire | North Northamptonshire | WPD_SM | North Northamptonshire WP3 | 0 | 0 | 0 | 10 | 0 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Central & Wales | Oxfordshire | Oxfordshire | WPD_SM | Oxfordshire WP1 | 165000 | 200000 | 200000 | 10 | 200 | 10 |  |  |  |  | 50 | 50 | 50 | 50 |  |  |  |  | 220 | 0 | 0 | 0 | 0 | 55 | 55 | 55 | 55 | 0 | 0 | 0 | 0
Central & Wales | Oxfordshire | Oxfordshire | WPD_SM | Oxfordshire WP2 | 162000 | 200000 | 200000 | 10 | 200 | 10 | [7 empty] | 50 | 50 | 50 | 50 |  | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 55 | 55 | 0
Central & Wales | Oxfordshire | Oxfordshire | WPD_SM | Oxfordshire WP3 | 15000 | 50000 | 50000 | 10 | 50 | 10 | [11 empty] | 50 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55
Central & Wales | Oxfordshire | Oxfordshire | WPD_SM | Oxfordshire WP4 | 0 | 0 | 0 | 10 | 0 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Central & Wales | Oxfordshire | Oxfordshire | WPD_SM | Oxfordshire WP5 | 0 | 0 | 0 | 10 | 0 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Central & Wales | Bedford | Bedford | WPD_SM | Bedford WP1 | 135000 | 150000 | 150000 | 10 | 150 | 10 | [8 empty] | 50 | 50 | 50 |  | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 55 | 0
Central & Wales | Bedford | Bedford | WPD_SM | Bedford WP2 | 0 | 0 | 0 | 10 | 0 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Central & Wales | Bedford | Bedford | WPD_SM | Bedford WP3 | 0 | 0 | 0 | 10 | 0 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Central & Wales | Gloucester - F&F | Gloucester - F&F | WPD_SM | Gloucester - F&F | 27000 | 50000 | 50000 | 10 | 50 | 10 |  |  | 50 | [9 empty] | 55 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Central & Wales | Gloucester - GCC LEVI WP3 | Gloucester - GCC LEVI WP3 | WPD_SM | Gloucester - GCC LEVI WP3 | 36000 | 100000 | 100000 | 10 | 100 | 10 |  | 50 | 50 | [9 empty] | 77 | 0 | 22 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Central & Wales | CCR | CCR | WPD_SM | CCR | 3000 | 50000 | 50000 | 10 | 50 | 10 |  | 50 | [10 empty] | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Central & Wales | Barking & Dagenham | Barking & Dagenham | WPD_SM | Barking & Dagenham | 24000 | 50000 | 50000 | 10 | 50 | 10 |  |  | 50 | [9 empty] | 55 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Central & Wales | Suffolk | Suffolk | WPD_SM | Suffolk | 9000 | 50000 | 50000 | 10 | 50 | 10 |  |  | 50 | [9 empty] | 55 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Central & Wales | Ceredigion | Ceredigion | WPD_SM | Ceredigion | 102000 | 100000 | 100000 | 10 | 100 | 10 |  |  | 50 | 50 | [8 empty] | 110 | 0 | 0 | 55 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Midlands | Midlands Connect - Leicestershire | Midlands Connect - Leicestershire | WPD_EM | Midlands Connect - Leicestershire WP1 | 127500 | 200000 | 200000 | 10 | 200 | 10 | [8 empty] | 50 | 50 | 50 | 50 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 55 | 55
Midlands | Midlands Connect - Leicestershire | Midlands Connect - Leicestershire | WPD_EM | Midlands Connect - Leicestershire WP2 | 52500 | 100000 | 100000 | 10 | 100 | 10 | [10 empty] | 50 | 50 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55
Midlands | Midlands Connect - Leicestershire | Midlands Connect - Leicestershire | WPD_EM | Midlands Connect - Leicestershire WP3 | 0 | 0 | 0 | 10 | 0 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Midlands | Midlands Connect - Leicestershire | Midlands Connect - Leicestershire | WPD_EM | Midlands Connect - Leicestershire WP4 | 0 | 0 | 0 | 10 | 0 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Midlands | Midlands Connect - Rutland | Midlands Connect - Rutland | WPD_EM | Midlands Connect - Rutland WP1 | 127500 | 200000 | 200000 | 10 | 200 | 10 | [8 empty] | 50 | 50 | 50 | 50 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 55 | 55
Midlands | Midlands Connect - Rutland | Midlands Connect - Rutland | WPD_EM | Midlands Connect - Rutland WP2 | 60000 | 100000 | 100000 | 10 | 100 | 10 | [10 empty] | 50 | 50 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55
Midlands | Midlands Connect - Warwickshire | Midlands Connect - Warwickshire | WPD_EM | Midlands Connect - Warwickshire WP1 | 165000 | 200000 | 200000 | 10 | 200 | 10 | [8 empty] | 50 | 50 | 50 | 50 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 55 | 55
Midlands | Midlands Connect - Warwickshire | Midlands Connect - Warwickshire | WPD_EM | Midlands Connect - Warwickshire WP2 | 0 | 0 | 0 | 10 | 0 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Midlands | Midlands Connect - Warwickshire | Midlands Connect - Warwickshire | WPD_EM | Midlands Connect - Warwickshire WP3 | 0 | 0 | 0 | 10 | 0 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Midlands | Midlands Connect - Warwickshire | Midlands Connect - Warwickshire | WPD_EM | Midlands Connect - Warwickshire WP4 | 0 | 0 | 0 | 10 | 0 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Midlands | Midlands Connect - Worcestershire | Midlands Connect - Worcestershire | WPD_EM | Midlands Connect - Worcestershire WP1 | 165000 | 200000 | 200000 | 10 | 200 | 10 | [8 empty] | 50 | 50 | 50 | 50 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 55 | 55
Midlands | Midlands Connect - Worcestershire | Midlands Connect - Worcestershire | WPD_EM | Midlands Connect - Worcestershire WP2 | 60000 | 100000 | 100000 | 10 | 100 | 10 | [10 empty] | 50 | 50 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55
Midlands | Midlands Connect - Worcestershire | Midlands Connect - Worcestershire | WPD_EM | Midlands Connect - Worcestershire WP3 | 0 | 0 | 0 | 10 | 0 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Midlands | Midlands Connect - Trojan | Midlands Connect - Trojan | WPD_EM | Trojan WPX | 0 | 0 | 0 | 10 | 0 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
North | Blackburn | Blackburn | SSEN_N | Blackburn WP1 | 150000 | 150000 | 150000 | 10 | 150 | 10 | [5 empty] | 50 | 50 | 50 |  |  |  |  | 165 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 55 | 0 | 0 | 0 | 0
North | Blackburn | Blackburn | SSEN_N | Blackburn WP2 | 132000 | 150000 | 150000 | 10 | 150 | 10 | [5 empty] | 50 | 50 | 50 |  |  |  |  | 165 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 55 | 0 | 0 | 0 | 0
North | Blackburn | Blackburn | SSEN_N | Blackburn WP3 | 168000 | 100000 | 100000 | 10 | 100 | 10 | [9 empty] | 50 | 50 |  | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 0
North | Warrington (LEVI Pilot) | Warrington (LEVI Pilot) | SSEN_N | Warrington | 225000 | 200000 | 200000 | 10 | 200 | 10 | [5 empty] | 50 | 50 | 50 | 50 |  |  |  | 220 | 0 | 0 | 0 | 0 | 0 | 55 | 55 | 55 | 55 | 0 | 0 | 0
North | Warrington (LEVI) | Warrington (LEVI) | SSEN_N | Warrington (LEVI) WPX | 0 | 0 | 0 | 10 | 0 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
North | Cheshire West & Chester | Cheshire West & Chester | SSEN_N | Cheshire West and Chester WP1 | 60000 | 100000 | 100000 | 10 | 100 | 10 | [10 empty] | 50 | 50 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 55
North | Cheshire West & Chester | Cheshire West & Chester | SSEN_N | Cheshire West and Chester WP2 | 0 | 0 | 0 | 10 | 0 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
North | Cheshire West & Chester | Cheshire West & Chester | SSEN_N | Cheshire West and Chester WP3 | 0 | 0 | 0 | 10 | 0 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
North | NECA - Gateshead | NECA - Gateshead | SSEN_N | NECA - Gateshead WPX | 0 | 0 | 0 | 10 | 0 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
North | NECA - Newcastle upon Tyne | NECA - Newcastle upon Tyne | SSEN_N | NECA - Newcastle upon Tyne WPX | 0 | 0 | 0 | 10 | 0 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
North | NECA - North Tyneside | NECA - North Tyneside | SSEN_N | NECA - North Tyneside WPX | 0 | 0 | 0 | 10 | 0 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
North | NECA - South Tyneside | NECA - South Tyneside | SSEN_N | NECA - South Tyneside WPX | 0 | 0 | 0 | 10 | 0 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
North | NECA - Sunderland | NECA - Sunderland | SSEN_N | NECA - Sunderland WPX | 0 | 0 | 0 | 10 | 0 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
North | NECA - Northumberland | NECA - Northumberland | SSEN_N | NECA - Northumberland WPX | 0 | 0 | 0 | 10 | 0 | 10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
North | Sunderland - LEVI | Sunderland - LEVI | SSEN_N | Sunderland - LEVI | 139500 | 200000 | 200000 | 10 | 200 | 10 |  |  | 50 | 50 | 50 | 50 | [6 empty] | 220 | 0 | 0 | 55 | 55 | 55 | 55 | 0 | 0 | 0 | 0 | 0 | 0
North | South Tyneside - Rapids - Levelling-up Fund | South Tyneside - Rapids - Levelling-up Fund | SSEN_N | South Tyneside - Rapids - Levelling-up Fund | 12000 | 300000 | 300000 | 10 | 300 | 10 | 50 | 50 | 50 | 50 | 50 | 50 | [6 empty] | 279 | 55 | 4 | 55 | 55 | 55 | 55 | 0 | 0 | 0 | 0 | 0 | 0
North | Westmorland and Furness Council | Westmorland and Furness Council | SSEN_N | Westmorland and Furness Council | 75000 | 200000 | 200000 | 10 | 200 | 10 |  |  | 50 | 50 | 50 | 50 | [6 empty] | 220 | 0 | 0 | 55 | 55 | 55 | 55 | 0 | 0 | 0 | 0 | 0 | 0
Commercial | Barratts | Barratts | WPD_SM | Barratts | 57000 | 50000 | 50000 | 10 | 50 | 10 | 50 | [11 empty] | 55 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commercial | Prologis | Prologis | WPD_SM | Prologis | 25500 | 50000 | 50000 | 10 | 50 | 10 |  |  | 50 | [9 empty] | 55 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Assumption
Value per socket | Assumption | Notes
capex_bom | 1000 | Bill of Materials
capex_installation | 1000 | On‑site build cost
capex_connection | 1000 | Getting power to site, include ICP (Independent Connection Provider) and DNO cost
capex | 3000
Asset Value | 1000
No. of sockets
Senior Delivery Manager annual capacity | 1000
Delivery Manger annual capacity | 500