## North and Scotland (hidden)
2026 Regional Programme Plan: North
Partner:
SDM: Chris Gorringe
Target: 1,200 Sockets
Workbank: 2,500 sockets
Work Package | Commissioned Sockets in 2026 | PDM | [52 empty] | Commissioned Sockets in 2027 | 2027 - Weeks
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
N Yorks - 01 | 124 | Clare Bennett | 11: 1; 27: 2; 28: 3; 44: 4
N Yorks - 02 |  | Clare Bennett | 11: 1; 33: 2; 34: 3 | 118 | [6 empty] | 4
N Yorks - 03 |  | Clare Bennett | 11: 1; 39: 2; 40: 3 | 118 | [21 empty] | 4
Blackburn & Darwen - 01 | 100 | Chris Gorringe | 9: 2; 13: 3; 28: 4
Blackburn & Darwen - 02 | 100 | Chris Gorringe | 1: 1; 14: 2; 18: 3; 31: 4
Blackburn & Darwen - 03 | 80 | Chris Gorringe | 1: 1; 19: 2; 23: 3; 35: 4
Warrington -01 | 50 | Taz Choudhury | 10: 2; 14: 3; 30: 4
Warrington - 02 | 50 | Taz Choudhury | 10: 2; 14: 3; 30: 4
Warrington - 03 | 50 | Taz Choudhury | 10: 2; 14: 3; 39: 4
Sunderland - 01 | 102 | Clare Bennett | 5: 2; 12: 3; 48: 4
Westmoreland - 01 | 45 | Taz Choudhury | 22: 4
Total Sockets in 2026 | 701 |  | 52: Total Sockets in 2026 | 236
|  |  |  | Critical Path | [9 empty] | Gate 1 -Site Selection handover
|  |  |  | Definition | [9 empty] | Gate 2 - Definition agreed with WP
|  |  |  | Governance | [9 empty] | Gate 3 - Build Financial Approval
|  |  |  | Survey & Design | [9 empty] | Gate 4 - Site Commissioned 100% complete
Install, Connection, Meter & Commission

## South (Marlon) (hidden)
2026 Regional Programme Plan: South
Partner:
SDM: Mitch Burgess
Target: 1,200 Sockets
Workbank: 2,500 sockets
Work Package | Commissioned Sockets in 2026/2027 | PDM | 2026 - Weeks | [51 empty] | 2027 - Weeks
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Plymouth WP1 | 140 | Marlon | bar: 2026 - Weeks 1 to 2026 - Weeks 41
Plymouth WP2 | 140 | Marlon | bar: 2026 - Weeks 10 to 2026 - Weeks 52
Plymouth WP3 | 140 | Marlon | bar: 2026 - Weeks 37 to 2026 - Weeks 52
Plymouth WP4 | 140 | Marlon
Plymouth WP5 | 140 | Marlon
Marlon
West Sussex Phase 4 WP1 | 20 | Marlon | bar: 2026 - Weeks 1 to 2026 - Weeks 15
West Sussex Car Parks V4 | 68 | Marlon | bar: 2026 - Weeks 1 to 2026 - Weeks 15
Total Sockets in 2026/2027 | 788
Critical Path
Definition
Governance
Design & Survey
Install, Connection, Meter & Commission

## South (hidden)
2026 Regional Programme Plan: South
Partner:
SDM: Mitch Burgess
Target: 1,200 Sockets
Workbank: 2,500 sockets
Region | Client | Contract | Work Package | Commissioned Sockets in 2026/2027 | PDM | 2026 - Weeks | [51 empty] | 2027 - Weeks
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
[6 empty] | Jan | Jan | Jan | Jan | Feb | Feb | Feb | Feb | Mar | Mar | Mar | Mar | Apr | Apr | Apr | Apr | Apr | May | May | May | May | Jun | Jun | Jun | Jun | Jul | Jul | Jul | Jul | Jul | Aug | Aug | Aug | Aug | Sep | Sep | Sep | Sep | Sep | Oct | Oct | Oct | Oct | Nov | Nov | Nov | Nov | Dec | Dec | Dec | Dec | Dec | Jan | Jan | Jan | Jan | Feb | Feb | Feb | Feb | Mar | Mar | Mar | Mar | Apr | Apr | Apr | Apr | Apr | May | May | May | May | Jun | Jun | Jun | Jun | Jul | Jul | Jul | Jul | Jul | Aug | Aug | Aug | Aug | Sep | Sep | Sep | Sep | Sep | Oct | Oct | Oct | Oct | Nov | Nov | Nov | Nov | Dec | Dec | Dec | Dec | Dec
South | Surrey | LEVI | 3 | 36 | Jamie Searl | bar: 2026 - Weeks 1 Jan to 2026 - Weeks 13 Apr
South | Surrey | LEVI | 4 | 14 | Jamie Searl | bar: 2026 - Weeks 1 Jan to 2026 - Weeks 13 Apr
South | Surrey | LEVI | 5 | 24 | Jamie Searl | bar: 2026 - Weeks 1 Jan to 2026 - Weeks 15 Apr
South | Surrey | LEVI | 6 | 26 | Jamie Searl | bar: 2026 - Weeks 1 Jan to 2026 - Weeks 15 Apr
South | Surrey | LEVI | 7 | 64 | Jamie Searl | bar: 2026 - Weeks 1 Jan to 2026 - Weeks 16 Apr
South | Surrey | LEVI | 8 | 88 | Jamie Searl | bar: 2026 - Weeks 1 Jan to 2026 - Weeks 24 Jun
South | Surrey | LEVI | 9 | 136 | Jamie Searl | bar: 2026 - Weeks 1 Jan to 2026 - Weeks 24 Jun
South | Surrey | LEVI | 10 | 206 | Jamie Searl | bar: 2026 - Weeks 1 Jan to 2026 - Weeks 22 Jun
South | Surrey | LEVI | 11 | 142 | Jamie Searl
South | Surrey | LEVI | 12 | 142 | Jamie Searl
South | Surrey | LEVI | 13 | 222 | Jamie Searl
South | Surrey | LEVI | 14 | 222 | Jamie Searl
|  |  | Total Sockets in 2026/2027 | 1322
Region | Client | Contract | Work Package | Commissioned Sockets in 2026/2027 | PDM | 2026 - Weeks 1 Jan: 2026 - Weeks
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
[6 empty] | Jan | Jan | Jan | Jan | Feb | Feb | Feb | Feb | Mar | Mar | Mar | Mar | Apr | Apr | Apr | Apr | Apr | May | May | May | May | Jun | Jun | Jun | Jun | Jul | Jul | Jul | Jul | Jul | Aug | Aug | Aug | Aug | Sep | Sep | Sep | Sep | Sep | Oct | Oct | Oct | Oct | Nov | Nov | Nov | Nov | Dec | Dec | Dec | Dec | Dec
South | Surrey |  | WP3 - Non Consultation |  | Marlon Brown | bar: 2026 - Weeks 1 Jan to 2026 - Weeks 35 Sep
South | Surrey |  | WP4 - Consultation |  | Marlon Brown | bar: 2026 - Weeks 1 Jan to 2026 - Weeks 39 Sep
Total Sockets in 2026/2027
Critical Path
Definition
Governance
Survey & Design
Install, Connection, Meter & Commission
Region | Client | Contract | Work Package | Commissioned Sockets in 2026/2027 | PDM | 2026 - Weeks 1 Jan: 2026 - Weeks | 2027 - Weeks
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
[6 empty] | Jan | Jan | Jan | Jan | Feb | Feb | Feb | Feb | Mar | Mar | Mar | Mar | Apr | Apr | Apr | Apr | Apr | May | May | May | May | Jun | Jun | Jun | Jun | Jul | Jul | Jul | Jul | Jul | Aug | Aug | Aug | Aug | Sep | Sep | Sep | Sep | Sep | Oct | Oct | Oct | Oct | Nov | Nov | Nov | Nov | Dec | Dec | Dec | Dec | Dec | Jan | Jan | Jan | Jan | Feb | Feb | Feb | Feb | Mar | Mar | Mar | Mar | Apr | Apr | Apr | Apr | Apr | May | May | May | May | Jun | Jun | Jun | Jun | Jul | Jul | Jul | Jul | Jul | Aug | Aug | Aug | Aug | Sep | Sep | Sep | Sep | Sep | Oct | Oct | Oct | Oct | Nov | Nov | Nov | Nov | Dec | Dec | Dec | Dec | Dec
South | Kent Parish |  | N/A | 8 | Jamie Searl | bar: 2026 - Weeks 1 Jan to 2026 - Weeks 14 Apr
South | Tonbridge & Malling |  | N/A | 36 | Jamie Searl | bar: 2026 - Weeks 1 Jan to 2026 - Weeks 14 Apr
South | LBBD |  | 1 | 58 | Jamie Searl | bar: 2026 - Weeks 1 Jan to 2026 - Weeks 14 Apr
South | LBBD |  | 2 | 8 | Jamie Searl | bar: 2026 - Weeks 1 Jan to 2026 - Weeks 14 Apr
South | Wealden |  | 1 | 28 | Jamie Searl | bar: 2026 - Weeks 1 Jan to 2026 - Weeks 14 Apr
South | Wealden |  | 2 | 14 | Jamie Searl | bar: 2026 - Weeks 1 Jan to 2026 - Weeks 14 Apr
South | West Sussex | Phase 4 | 1 | 20 | Marlon Brown | bar: 2026 - Weeks 1 Jan to 2026 - Weeks 15 Apr
South | West Sussex | Car Parks | 4 | 68 | Marlon Brown | bar: 2026 - Weeks 1 Jan to 2026 - Weeks 15 Apr
|  |  | Total Sockets in 2026/2027 | 240
Critical Path
Definition
Governance
Survey & Design
Install, Connection, Meter & Commission
Region | Client | Contract | Work Package | Commissioned Sockets in 2026/2027 | PDM | 2026 - Weeks 1 Jan: 2026 - Weeks | 2027 - Weeks
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
[6 empty] | Jan | Jan | Jan | Jan | Feb | Feb | Feb | Feb | Mar | Mar | Mar | Mar | Apr | Apr | Apr | Apr | Apr | May | May | May | May | Jun | Jun | Jun | Jun | Jul | Jul | Jul | Jul | Jul | Aug | Aug | Aug | Aug | Sep | Sep | Sep | Sep | Sep | Oct | Oct | Oct | Oct | Nov | Nov | Nov | Nov | Dec | Dec | Dec | Dec | Dec | Jan | Jan | Jan | Jan | Feb | Feb | Feb | Feb | Mar | Mar | Mar | Mar | Apr | Apr | Apr | Apr | Apr | May | May | May | May | Jun | Jun | Jun | Jun | Jul | Jul | Jul | Jul | Jul | Aug | Aug | Aug | Aug | Sep | Sep | Sep | Sep | Sep | Oct | Oct | Oct | Oct | Nov | Nov | Nov | Nov | Dec | Dec | Dec | Dec | Dec
South | Plymouth | LEVI | 1 | 110 | Marlon | bar: 2026 - Weeks 1 Jan to 2026 - Weeks 40 Oct
South | Plymouth | LEVI | 2 | 110 | Marlon | bar: 2026 - Weeks 10 Mar to 2026 - Weeks 52 Dec
South | Plymouth | LEVI | 3 | 110 | Marlon | bar: 2026 - Weeks 37 Sep to 2026 - Weeks 52 Dec
South | Plymouth | LEVI | 4 | 110 | Marlon
South | Plymouth | LEVI | 5 | 110 | Marlon
South | BCP and Dorset | LEVI | 1 | 150 | Jamie | bar: 2026 - Weeks 5 Feb to 2026 - Weeks 44 Nov
South | BCP and Dorset | LEVI | 2 | 150 | Jamie | bar: 2026 - Weeks 14 Apr to 2026 - Weeks 52 Dec
South | BCP and Dorset | LEVI | 3 | 150 | Jamie | bar: 2026 - Weeks 23 Jun to 2026 - Weeks 52 Dec
South | BCP and Dorset | LEVI | 4 | 150 | Jamie | bar: 2026 - Weeks 32 Aug to 2026 - Weeks 52 Dec
|  |  | Total Sockets in 2026/2027 | 850

## Midlands Connect (hidden)
2026 Regional Programme Plan: Midlands Connect 4
Partner: Circet/EJC
SDM: Mark Richards
Target: 1,200 Sockets
Workbank: 2,500 sockets
Region | Client | Contract | Work Package | Sites | Commissioned Sockets in 2026 | Commissioned Sockets in 2027 | PDM | 2026 - Weeks | [51 empty] | 2026 - Weeks
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
[8 empty] | Jan | Jan | Jan | Jan | Feb | Feb | Feb | Feb | Mar | Mar | Mar | Mar | Apr | Apr | Apr | Apr | Apr | May | May | May | May | Jun | Jun | Jun | Jun | Jul | Jul | Jul | Jul | Jul | Aug | Aug | Aug | Aug | Sep | Sep | Sep | Sep | Sep | Oct | Oct | Oct | Oct | Nov | Nov | Nov | Nov | Dec | Dec | Dec | Dec | Dec | Jan | Jan | Jan | Jan | Feb | Feb | Feb | Feb | Mar | Mar | Mar | Mar | Apr | Apr | Apr | Apr | Apr | May | May | May | May | Jun | Jun | Jun | Jun | Jul | Jul | Jul | Jul | Jul | Aug | Aug | Aug | Aug | Sep | Sep | Sep | Sep | Sep | Oct | Oct | Oct | Oct | Nov | Nov | Nov | Nov | Dec | Dec | Dec | Dec | Dec
Midlands Connect | Leicestershire | 100/400/300 | WP1 | 25 | 100 |  | Josh S | bar: 2026 - Weeks 9 Mar to 2026 - Weeks 38 Sep
Midlands Connect |  |  | WP2 | 25 | 100 |  | Josh S | bar: 2026 - Weeks 14 Apr to 2026 - Weeks 43 Oct
Midlands Connect |  |  | WP3 | 25 | 100 |  | Josh S | bar: 2026 - Weeks 19 May to 2026 - Weeks 48 Dec
Midlands Connect |  |  | WP4 | 25 | 52 | 48 | Josh S | bar: 2026 - Weeks 24 Jun to 2026 - Weeks 51 Dec; 2026 - Weeks 1 Jan to 2026 - Weeks 2 Jan
Midlands Connect
Midlands Connect
Midlands Connect | Rutland | 45/180/135 | WP1 | 25 | 100 | bar: 2026 - Weeks 9 Mar to 2026 - Weeks 38 Sep
Midlands Connect |  |  | WP2 | 20 | 80 | bar: 2026 - Weeks 14 Apr to 2026 - Weeks 43 Oct
Midlands Connect
Midlands Connect
Midlands Connect | Warwickshire | 115/460/330 | WP1 | 30 | 120 | bar: 2026 - Weeks 9 Mar to 2026 - Weeks 38 Sep
Midlands Connect |  |  | WP2 | 30 | 120 | bar: 2026 - Weeks 14 Apr to 2026 - Weeks 43 Oct
Midlands Connect |  |  | WP3 | 30 | 120 | bar: 2026 - Weeks 19 May to 2026 - Weeks 48 Dec
Midlands Connect |  |  | WP4 | 25 | 52 | 48 | bar: 2026 - Weeks 24 Jun to 2026 - Weeks 51 Dec; 2026 - Weeks 1 Jan to 2026 - Weeks 2 Jan
Midlands Connect
Midlands Connect | Worcestershire | 90/360/270 | WP1 | 30 | 120 | bar: 2026 - Weeks 9 Mar to 2026 - Weeks 38 Sep
Midlands Connect |  |  | WP2 | 30 | 120 | bar: 2026 - Weeks 14 Apr to 2026 - Weeks 43 Oct
Midlands Connect |  |  | WP3 | 30 | 120 | bar: 2026 - Weeks 19 May to 2026 - Weeks 48 Dec
Midlands Connect
Midlands Connect | Cambridge |  |  | 2 | 72 | bar: 2026 - Weeks 1 Jan to 2026 - Weeks 17 Apr
Midlands Connect
Midlands Connect | Suffolk Retrofit | bar: 2026 - Weeks 1 Jan to 2026 - Weeks 11 Mar
Midlands Connect
Midlands Connect | Gloucestershire | LEVI | WP2 | 9 | 36 |  | Josh S | bar: 2026 - Weeks 1 Jan to 2026 - Weeks 8 Feb
Midlands Connect | Gloucestershire | LEVI | WP3 | 13 | 52 |  | Josh S | bar: 2026 - Weeks 1 Jan to 2026 - Weeks 8 Feb
|  |  | Total Sockets in 2026 | 374 | 1464 | 96
Critical Path
Definition
Governance
Survey & Design
Install, Connection, Meter & Commission

## Central & Wales (hidden)
2026 Regional Programme Plan: Central & Wales
Partner: CIRCET & EJC
SDM: Christopher Clack
Target: 1200 Sockets
Workbank: 3,138 Sockets
Region | Client | Contract | Work Package | Commissioned Sockets in 2026 | Commissioned Sockets in 2027 | PDM | 2026 - Weeks
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
[7 empty] | Jan | Jan | Jan | Jan | Feb | Feb | Feb | Feb | Mar | Mar | Mar | Mar | Apr | Apr | Apr | Apr | Apr | May | May | May | May | Jun | Jun | Jun | Jun | Jul | Jul | Jul | Jul | Jul | Aug | Aug | Aug | Aug | Sep | Sep | Sep | Sep | Sep | Oct | Oct | Oct | Oct | Nov | Nov | Nov | Nov | Dec | Dec | Dec | Dec | Dec
Central and Wales | Oxfordshire | LEVI | 1 | 120 |  | TBC | bar: 2026 - Weeks 1 Jan to 2026 - Weeks 29 Jul
Central and Wales | Oxfordshire | LEVI | 2 | 120 |  | TBC | bar: 2026 - Weeks 5 Feb to 2026 - Weeks 34 Aug
Central and Wales | Oxfordshire | LEVI | 3 | 120 |  | TBC | bar: 2026 - Weeks 9 Mar to 2026 - Weeks 39 Sep
Central and Wales | Oxfordshire | LEVI | 4 | 120 |  | TBC | bar: 2026 - Weeks 13 Apr to 2026 - Weeks 43 Oct
Central and Wales | Oxfordshire | LEVI | 5 | 120 |  | TBC | bar: 2026 - Weeks 17 Apr to 2026 - Weeks 47 Nov
Central and Wales | Oxfordshire | LEVI | 6 | Year 2 |  | TBC
Central and Wales | Oxfordshire | LEVI | 7 | Year 2 |  | TBC
Central and Wales | Oxfordshire | LEVI | 8 | Year 2 |  | TBC
Central and Wales | Oxfordshire | LEVI | 9 | Year 3 |  | TBC
Central and Wales | West Berkshire | LEVI | 1 | 120 |  | TBC | bar: 2026 - Weeks 1 Jan to 2026 - Weeks 31 Aug
Central and Wales | West Berkshire | LEVI | 2 | 120 |  | TBC | bar: 2026 - Weeks 5 Feb to 2026 - Weeks 35 Sep
Central and Wales | West Berkshire | LEVI | 3 | 120 |  | TBC | bar: 2026 - Weeks 9 Mar to 2026 - Weeks 39 Sep
Central and Wales | West Berkshire | LEVI | 4 | Year 2 |  | TBC
Central and Wales | West Berkshire | LEVI | 5 | Year 2 |  | TBC
Central and Wales | West Berkshire | LEVI | 6 | Year 3 |  | TBC
Central and Wales | West Berkshire | LEVI | 7 | Year 3 |  | TBC
Central and Wales | West Berkshire | LEVI | 8 | Year 4 |  | TBC
Central and Wales | North Northamptonshire | LEVI | 1 | 120 |  | TBC | bar: 2026 - Weeks 1 Jan to 2026 - Weeks 31 Aug
Central and Wales | North Northamptonshire | LEVI | 2 | 120 |  | TBC | bar: 2026 - Weeks 5 Feb to 2026 - Weeks 35 Sep
Central and Wales | North Northamptonshire | LEVI | 3 | 120 |  | TBC | bar: 2026 - Weeks 9 Mar to 2026 - Weeks 39 Sep
Central and Wales | North Northamptonshire | LEVI | 4 | Year 2 |  | TBC
Central and Wales | North Northamptonshire | LEVI | 5 | Year 3 |  | TBC
Central and Wales | North Northamptonshire | LEVI | 6 | Year 4 |  | TBC
Central and Wales | Bedford | LEVI | 1 | 120 |  | TBC | bar: 2026 - Weeks 1 Jan to 2026 - Weeks 31 Aug
Central and Wales | Bedford | LEVI | 2 | 120 |  | TBC | bar: 2026 - Weeks 5 Feb to 2026 - Weeks 35 Sep
Central and Wales | Bedford | LEVI | 3 | 120 |  | TBC | bar: 2026 - Weeks 9 Mar to 2026 - Weeks 39 Sep
Central and Wales | Bedford | LEVI | 4 | Year 2 |  | TBC
Central and Wales | Bedford | LEVI | 5 | Year 2 |  | TBC
Central and Wales | Bedford | LEVI | 6 | Year 2 |  | TBC
Central and Wales | Bedford | LEVI | 7 | Year 3 |  | TBC
Central and Wales | Bedford | LEVI | 8 | Year 3 |  | TBC
Central and Wales | Ceredigion | TFW | 1 | 72 |  | Chris Clack | bar: 2026 - Weeks 1 Jan to 2026 - Weeks 13 Apr
|  |  | Total Sockets in 2026 | 1752
Critical Path
Definition
Governance
Survey & Design
Install, Connection, Meter & Commission

## Sheet1
Work Package | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Name | [5 empty] | 1 | [11 empty] | 2 |  |  |  |  | 3 | [15 empty] | 4